## Sheet1
| Diagnostic Phase | Analysis Phase | Design Phase | Development Phase | Deployment Phase | Operation Phase
Tasks | 1. Evaluate a customer's business processes and infrastructure 2. Assist the customer with their due diligence cycle, including ascertaining requirements and their fit with the solution, and assessing the resource needs for the solution deliver 3. Prepare the project plan, proposal, and the Statement of Work | 1. Analyze current business model and finalize the Functional Requirements document 2. Finalize the fit-gap analysis 3. Develop the Environment Specification documentation | 1. Develop the Functional Design, Technical Design, and Solution Design documents 2. Finalize the data migration design 3. Establish test criteria | 1. Finalize configurations and setup of the standard solution 2. Develop and finalize the custom code that is required to support the solution 3. Conduct functional and feature testing of the solution 4. Create the user training documentation | 1. Set up the production environment 2. Migrate data to the production environment 3. Conduct user acceptance test of the system 4. Train users and finalize the user documentation 5. Conduct go-live check and promote the system to production | 1. Resolve pending issues 2. Finalize user documentation and knowledge transfer 3. Conduct a post-mortem of the project 4. Provide on-going support (activities that continue through any future involvement with the customer after the project is closed)
Best Practices | 1. Engage key stakeholders 2. Conduct thorough business process analysis 3. Identify pain points and opportunities 4. Develop a clear business case and ROI analysis 5. Establish strong project governance | 1. Define clear requirements and expectations 2. Conduct fit-gap analysis 3. Develop a comprehensive data migration plan 4. Identify integration points 5. Establish clear scope and timeline | 1. Develop flexible and scalable design 2. Consider industry best practices 3. Ensure data integrity and security 4. Plan for future upgrades 5. Conduct design reviews | 1. Follow Microsoft coding standards 2. Conduct unit testing and debugging 3. Ensure data migration quality 4. Use automated testing tools 5. Document customizations | 1. Comprehensive deployment plan 2. Thorough testing and quality assurance 3. Go-live support and training 4. Data backup and recovery processes 5. Post-deployment review | 1. Support and maintenance plan 2. Monitor system performance 3. Regular updates and backups 4. Ongoing training and user support 5. Continuous improvement
Success Factors | 1. Clear understanding of business requirements 2. Strong stakeholder buy-in 3. Well-defined project scope 4. Realistic expectations 5. Effective project team formation | 1. Accurate requirements gathering 2. Effective solution design 3. Clear understanding of data migration needs 4. Identified risks and mitigation strategies 5. Realistic project timeline | 1. Well-designed solution architecture 2. Effective data model design 3. Clear understanding of customization needs 4. Identified potential roadblocks 5. Alignment with business objectives | 1. High-quality code development 2. Effective testing and quality assurance 3. Smooth data migration 4. Minimal defects 5. On-time delivery | 1. Smooth go-live experience 2. Minimal downtime 3. Effective user training 4. Successful data migration 5. Issue-free deployment | 1. High system uptime 2. Effective issue resolution 3. Continuous user adoption 4. Improved business processes 5. Realized ROI