## Playbook
PROJECT PLAYBOOK "Microsoft Dynamics 365 Business Central Implementation" |  | Version: 2.0
PROJECT PHASE | ACTIVITIES | DETAILS | DOCUMENT / ARTIFACT | RESPONSIBLE
1. PROJECT INITIATION | Stakeholder Analysis: Create overview of project stakeholders | Stakeholders in a Dynamics 365 implementation may include (depending on your business and the Dynamics license chosen): - Finance and Accounting - Sales & Marketing - Purchasing - Logistics & Warehouse Management - Production - Project Management - IT - Product Data Management - HR - Legal - Customers, Vendors - Shipping agents | Stakeholder Matrix | Project Management
| Setup project team | Nominate project manager and members representing each business function and stakeholder group; clarify roles and responsibilities | Roles & Responsibilities overview | Management
| Define project goal (and key objectives) | What issues exist with the current business processes that should be addressed in the project? E.g. process issues, communication issues, data quality issues, technical issues | Project Charter | Project team
How can the current issues be avoided? How could processes be improved (either through better organization/communication or by implementing Dynamics)?
Define the project goal and key objectives for the project
Define performance targets to be achieved by the project
| Define high-level scope | - Processes to be migrated to Dynamics - What processes should be reviewed and improved as part of the D365 project? - Applications/system to keep or to phase out as part of the project - Data cleansing - Integration needs (e.g. interfaces with ERP system or external parties) - Strategic requirements (with respect to business strategy + IT strategic) | Project Charter | Project Team
| Choose Dynamics license | Microsoft offers different "packages" for Dynamics 365. Choose the right license for your needs. | Software Licensing Agreement | Project Team
| Select Implementation Partner | Research specialty of implementation partner - should have experience in your industry/business model; sign contract | Service Contract | Project Team
2. PLANNING PHASE | Create Project Schedule | Create a detailed project timeline showing the five phases (initiation, planning, execution, closing) and lock in dates start and finish dates for the high-level activities. In particular, the dates for end-user testing should be confirmed early on. Use the included Gantt Chart as a template. | Project Schedule | Project Manager
| Create Project Budget | Set up a project budget using your tool of choice. Key budget items are labor cost, implementation service cost, licensing fees, hardware cost, travel expense | Project Budget | Project Manager
| Perform risk assessment | Perform a risk assessment together with your team and identify the key risks for the project itself but also for the involved business functions. | Risk Log | Project Team
| Finish Project Charter | Finish the Project Charter and have it signed by the client and partner. Key points to incude: Project overview and scope, risk assessment, timeline, budget, project team | Project Charter | Project Team
| Project Kickoff Meeting | Hold a formal kickoff meeting with all project contributors and stakeholders. Management should be attending the kickoff too. No excuses, this is a critical project! | Project Kickoff Slide Deck | Project Manager
3. DISCOVERY PHASE | Gather requirements | Together with process experts from the functional teams, the project team needs to work out the specific requirements for each area. Below you can find the key questions that must be discussed for each functional area. The requirements should be documented in a Business Requirement Specification document. | Requirement Specification | Project Team
| General questions | What does the current application landscape look like? Which systems are used and what is their purpose? | Requirement Specification | Project Team
|  | Who is in charge of maintaining those systems? | Requirement Specification | Project Team
|  | Which systems should be kept and which ones should be replaced with Dynamics? | Requirement Specification | Project Team
|  | What languages should the Dynamics user interface appear in? | Requirement Specification | Project Team
| Finance | What Chart of Accounts (ChoA) is used? | Requirement Specification | Project Team
|  | Which payment methods are used to pay vendor invoices? For example bank, cheque, cash, account etc. | Requirement Specification | Project Team
|  | Which payment terms are used? Applies to both, customer payments and payments to vendors | Requirement Specification | Project Team
|  | What are suitable designations to categorize postings? Typical categories are: Customer, Vendor, Inventory, Tax, Bank, General postings | Requirement Specification | Project Team
|  | What financial reports are created? What is their purpose? Gather examples | Requirement Specification | Project Team
|  | What tolerance levels should be applied for verifying payments? | Requirement Specification | Project Team
|  | Which accounting periods are used? 12 + 1? 12+2 etc? | Requirement Specification | Project Team
|  | When does the fiscal year start and end? | Requirement Specification | Project Team
|  | Do you collect and report Value Added Tax (VAT)? | Requirement Specification | Project Team
|  | How do you report VAT to authorities? | Requirement Specification | Project Team
|  | Which currencies do you trade in or report transactions in? | Requirement Specification | Project Team
|  | Which is the main reporting currency? | Requirement Specification | Project Team
|  | How do you receive exchange rate information? Manual entry or via interface? | Requirement Specification | Project Team
|  | Any country-specific processes or legislation that must be considered? | Requirement Specification | Project Team
|  | Any other financial documents or statements that are being used? | Requirement Specification | Project Team
|  | Which bank accounts are used? What is their purpose? Create account overview | Requirement Specification | Project Team
|  | Fixed assets: Prepare list of all "active" fixed assets (asset master) | Requirement Specification | Project Team
|  | Is there a special process for procurement of fixed assets? | Requirement Specification | Project Team
| Sales | Create an overview of all customers (Excel) | Requirement Specification | Project Team
|  | Decide on what customers to migrate to D365. For example, you could check which customers you have sold to in the last 24 months and migrate only those "active" customers to the new system. This can significantly reduce the migration effort, because whatever data is migrated to the new system first needs to be reviewed by the business team. | Requirement Specification | Project Team
|  | What type of products and/or services are being sold? | Requirement Specification | Project Team
|  | Do you only sell to domestic customers or also foreign customers? | Requirement Specification | Project Team
|  | What information is stored about customers? Create an overview with the data fields used and some sample records | Requirement Specification | Project Team
|  | Where do you currently keep your customer master data? E.g. Excel, other system, … | Requirement Specification | Project Team
|  | What payment methods do you use to receive customer payments? | Requirement Specification | Project Team
|  | How do you currently track sales performance for your sales team? | Requirement Specification | Project Team
|  | How do you currently manage pricing information? What system? | Requirement Specification | Project Team
|  | What pricing strategy is used? E.g. bulk pricing, discounts for particular customer groups etc. --> Document pricing strategy for each product or service category | Requirement Specification | Project Team
|  | Gather sample invoices showing the required layout and content | Requirement Specification | Project Team
|  | What documents or forms are used in sales? | Requirement Specification | Project Team
|  | What reports are used in sales? | Requirement Specification | Project Team
|  | Which shipment methods are used? | Requirement Specification | Project Team
|  | Which shipping agents do you work with? | Requirement Specification | Project Team
|  | What communication methods are used for client communication? Email, regular mail, fax … | Requirement Specification | Project Team
| Purchasing | Create an overview of all vendors (Excel) | Requirement Specification | Project Team
|  | Decide on what vendors to migrate to D365. For example, you could check which vendors you have bought from in the last 24 months and migrate only those "active" vendors to the new system. This can significantly reduce the migration effort, because whatever data is migrated to the new system first needs to be reviewed by the business team. | Requirement Specification | Project Team
|  | Do you work only work with domestic vendors or also foreign vendors? | Requirement Specification | Project Team
|  | What products or services do you procure? | Requirement Specification | Project Team
|  | Do you import goods from abroad? | Requirement Specification | Project Team
|  | Is there a country-specific import process that must be followed? | Requirement Specification | Project Team
|  | Create an overview of all purchasers (purchaser name, product category, assigned vendors) | Requirement Specification | Project Team
|  | Create list with vendor bank accounts (must be setup in D365) | Requirement Specification | Project Team
|  | Create overview with prices and discounts per vendor | Requirement Specification | Project Team
|  | What documents are used in purchasing? E.g. Purchase agreements, purchase order, shipment notifications, EDI documents etc. Gather samples of those documents | Requirement Specification | Project Team
|  | What approval strategy is used for purchasing? Do you have a workflow? What are the approval limits? | Requirement Specification | Project Team
| Inventory Management | What is the warehouse layout? What are the locations used? What numbering logic or designation is used for warehouse locations? | Requirement Specification | Project Team
|  | What type of items are stored in the warehouse? E.g. finished goods, goods for resale, raw material, work in progress (WIP) etc. | Requirement Specification | Project Team
|  | Define an appropriate system to categorize items (products). Item categories make it easier to search and find the right items. Also, item categories are used for reporting. A basic categorization could be: Indoor furniture, outdoor furniture | Requirement Specification | Project Team
|  | Do you work with product variantes? E.g. furniture of different color, products for different target audiences etc. | Requirement Specification | Project Team
|  | What product attributes are used for products? Attributes can be used to manage your product catalog or they may be shown to customers via your website. E.g. Model year, width, height, weight, country of origin etc. | Requirement Specification | Project Team
|  | Should users be required to specify the storage location of an item? | Requirement Specification | Project Team
|  | What costing method is used to track inventory value? E.g. LIFO, FIFO, averages or any other custom method? | Requirement Specification | Project Team
|  | If cost averaging is used, what period is used for calcuation of averages? Week? month, quarter, year etc.? | Requirement Specification | Project Team
|  | Should material movements automatically be posted into accounting? This is primarily a performance topic. When you have a lot of goods movements, you can setup the accounting postings to be done in a batch process outside of business hours. | Requirement Specification | Project Team
|  | What G/L accounts are used for inventory management? Provide an account overview with the used accounts for raw materials, WIP, finished goods, goods for resale and other items stored. | Requirement Specification | Project Team
|  | What numbering system is used for inventory items? | Requirement Specification | Project Team
|  | Do you use bills of material (BOMs)? If yes, how are BOMs currently managed? In Excel or any other tool? | Requirement Specification | Project Team
| Project Management | Is your company engaged in a project-based business where you deliver services or solutions to clients in the form of projects? For example: Custom equipment design, website development, construction | Requirement Specification | Project Team
|  | Are you performing projects internally to in-house clients? | Requirement Specification | Project Team
|  | What tool is currently used for project scheduling and cost tracking? Do you want to use Dynamics 365 for project management? | Requirement Specification | Project Team
|  | The following quiestions are only relevant if you decide to use Project Management in Business Central: | Requirement Specification | Project Team
|  | What types of projects do you run? What would be a suitable categories? For example: Assembly projects, repair projects, training projects, IT projects (in-house), projects purely used for cost tracking purposes etc. | Requirement Specification | Project Team
|  | What numbering system are used for projects? If none exists, define a system. | Requirement Specification | Project Team
|  | What reports are currently used in project management? | Requirement Specification | Project Team
|  | Do you want to use time-tracking on projects? | Requirement Specification | Project Team
|  | What are common project roles in your projects? For example: Project Manager, Project Engineer, Project Planner, QA Engineer, Training Expert, Data Security Officer | Requirement Specification | Project Team
|  | What resources are used in projects? E.g. people, equipment (what kind of), rooms or other facilities? | Requirement Specification | Project Team
|  | Define cost rates for resources used in (or involved in) projects. E.g. $120/hour | Requirement Specification | Project Team
|  | Do you have any approval workflow required for project management? | Requirement Specification | Project Team
| Customer Relationship Management | How do you currently manage and track your sales efforts and interactions with (potential) clients? | Requirement Specification | Project Team
|  | What contact / customer information do you store? | Requirement Specification | Project Team
|  | How do you segment your contacts? E.g. by industry segment, business size etc. | Requirement Specification | Project Team
|  | How do you currently manage and track sales opportunities? | Requirement Specification | Project Team
|  | What are the typical stages in the sales cycle? Think about the initial contact, qualification of customers, assignment to the right sales group etc. In Dynamics, you can easily track the stage of prospective customers. | Requirement Specification | Project Team
|  | Should inbound and outbound client communication automatically be retrieved from the email messaging system and tracked in Dynamics? | Requirement Specification | Project Team
| Human Resources | Create overview of all current employees (for import into Dynamics BC) | Requirement Specification | Project Team
|  | Do you want to show your employees' pictures in Dynamics? If yes, gather pictures | Requirement Specification | Project Team
|  | Would you like to track employee absences in Dynamics? | Requirement Specification | Project Team
| Warehouse Management | Warehouse Management in Dynamics allows for the detailed tracking of items on a zone and bin level, including all movements. The customer must decide whether they want to use this kind of detailed tracking of goods movements (which requires more effort in the system) of if they just want to use basic stock functionality. | Requirement Specification | Project Team
|  | What is your warehouse layout? Define the desired warehouse layout incl. zones for various purposes | Requirement Specification | Project Team
|  | Define warehouse bin types | Requirement Specification | Project Team
|  | What is the putaway process? | Requirement Specification | Project Team
|  | Prepare Excel file with warehouse employees | Requirement Specification | Project Team
|  | Define bin locations | Requirement Specification | Project Team
| Manufacturing | Are you have a manufacturing operation? | Requirement Specification | Project Team
|  | What does the manufacturing process(es) look like? Map out the process incl. Replenishment of input material and routing of finished goods | Requirement Specification | Project Team
|  | What work calendars are used for the resources used in manufacturing? For example, work calendars for machines, work centers or equipment | Requirement Specification | Project Team
|  | How do you currently manage production BOMs? Excel or any other tool? | Requirement Specification | Project Team
|  | BOMs to be migrated to Dynamics need to be reviewed and cleaned up | Requirement Specification | Project Team
|  | What lot sizes are used in production? | Requirement Specification | Project Team
|  | Do you have subcontract manufacturing agreements with some vendors? | Requirement Specification | Project Team
| Service Management | Are you offering services to your clients? What kinds of services? Services could be for example repair, testing, customization or training services | Requirement Specification | Project Team
|  | How do you currently manage service contracts? Which tool is used? | Requirement Specification | Project Team
|  | Map out each service process in a flow chart | Requirement Specification | Project Team
|  | Do you maintain a troubleshooting database for your service team? | Requirement Specification | Project Team
|  | How are these services priced? Do you have special pricing arrangements? | Requirement Specification | Project Team
|  | What are the office hours for your service team? | Requirement Specification | Project Team
| Approval workflows | Dynamics provides built-in electronic approval workflows which are very convenient and which can replace paper-based approval processes. It's a good idea to check with all departments whether they would like to use any system-supported approval workflows. | Requirement Specification | Project Team
| Interfaces | What system interfaces have to be established? | Requirement Specification | Project Team
|  | Who will perform the interface development? | Requirement Specification | Project Team
|  | Who will take over the ongoing interface monitoring? After go-live, somebody needs to look into the interface status and intervene in case of errors. | Requirement Specification | Project Team
| Finish Disover Phase, complete the Requirement Specification document | Requirements are now documented in a Business Requirement Specification Document. The document must be reviewed and signed by the client. | Requirement Specification | Project Team
4. DESIGN PHASE | Create Solution Design Document | The Implementation Partner will now create the Solution Design Document (SDD), which describes how business requirements gathered in the Discovery Phase will be implemented in the system | Solution Design Document | Implementation Partner
| Solution Design Document Review | Once the Implementation Partner has finished the Solution Design Document, he should walk the Customer through the document and explain how the Dynamics system will be set up to fulfil the customer's business requirements. The customer team should verify whether the requirements were correctly understood and if the intended system configuration seems plausible with respect to the business needs. | Solution Design Document | Customer, Implementation Partner
| Review effort estimation | Review effort estimation together with the customer, for the implementation of gaps as well as the standard configuration [gaps = any requirements that cannot be technically implemented within the standard solution; custom development necessary] | - | Customer, Implementation Partner
| Solution Design Document Sign-off | Solution Design Document (SDD) Signed off (by customer) | Solution Design Document | Customer, Implementation Partner
5. DEVELOPMENT | Create Development Environment | The Implementation Team will setup the development environment for Microsoft Dynamics | - | Implementation Partner
| Create User Overview | The Customer will provide an Excel file with the users to be set up in Dynamics | User Template | Customer
| Create User Accounts | Create needed user accounts in test system, assign appropriate permissions | User Template | Implementation Partner
| Provide initial data for system setup | The Implementation Partner will require certain data from the customer in order to set up the system as needed. Discuss with Implementation Partner what input is required. | Partner specific templates | Customer, Implementation Partner
| System configuration | The Implementation Partner will prepare the Dynamics system based on the agreed scope and requirements | - | Implementation Partner
| System configuration (Business Central Essentials Licence) | Component setup: Financial Management | - | Implementation Partner
|  | Component setup: Sales | - | Implementation Partner
|  | Component setup: Purchasing | - | Implementation Partner
|  | Component setup: Warehouse Management | - | Implementation Partner
|  | Component setup: CRM | - | Implementation Partner
|  | Component setup: Human Resources Management | - | Implementation Partner
|  | Component setup: Projects | - | Implementation Partner
| System configuration (Business Central Premium Licence) | Component setup: Business Central Essentials | - | Implementation Partner
|  | Component setup: Service | - | Implementation Partner
|  | Component setup: Manufacturing | - | Implementation Partner
| Custom development | Perform custom development if required | - | Implementation Partner
| Test data | Perform initial data import: Load a first set of master data (and other data to be migrated) into the Dynamics test system. For example a subset of customers, vendors, employees and other data objects. This initial upload is usually only done for testing purpose because we need test data in order to carry out the system and process tests. | User Template Vendor Template Customer Template + further templates provided by Partner | Customer, Implementation Partner
| Define Test Cases for Functional Test | The Customer team should define the relevant test cases for all areas -- Finance, Accounting, Sales, Purchasing -- with assistance by the Implementation Partner. Make sure all processes, scenarios and scenario variants are covered. For example, you may have a scenario "Enter purchase order". For a complete test, you want to the test various variants of that scenario -- purchases of different material types, purchase of services, buying from suppliers in other countries etc. | Test Case Template | Customer, Implementation Partner
| Perform Functional Test | Focus of the Functional Test is to verify whether all needed functionality and features in Dynamics are working properly: Can we create a purchase order? Can we print an invoice? Can we create a sales order, Can we book goods receipt for a PO etc. Tip: Have your testers (from the functional teams) sign a sheet confirming that all relevant scenarios have been tested successfully and the system works as requested. | - | Customer, Implementation Partner
6. DEPLOYMENT PHASE | Define Test Cases for User Acceptance Test + Integration Test | Define new test cases that reflect the complete process cycle for each process, from start to finish and with contribution of all departments involved in the process. For example, in the Integration Test, you would not just test the creation of a sales order, but also all subsequent steps such as picking from stock, creation of shipment documents, shipping, invoicing receipt of customer payment and clearing of the open item in accounts receivable. In the same fashion, you test all the other processes from start to finish. | Test Case Template | Customer, Implementation Partner
| Environment deployment for UAT + IT | Deploy test environment for UAT (User Acceptance Test) and IT (Integration Test)* *Discuss with your Partner what tests should be carried out. This depends on the system scope, the readiness of the organization and the users, the complexity of the migration and other factors. | - | Implementation Partner
| Perform UAT and System Integration Test | Carry out UAT and Integration Test - see above comment Tip: Have your testers (from the functional teams) sign a sheet confirming that all relevant scenarios have been tested successfully and the system works as requested. | - | Customer, Implementation Partner
| Approval of system configuration and test results | The Customer confirms that tests have been carried out successfully and the system works as required and all processes are covered. The system is technically setup for go-live. | Test Approval Sheet | Customer, Implementation Partner
7. GO-LIVE | Cut-over Planning | The Implementation Partner and Customer together will create a detailed plan for the actual system transition and go-live (cut-over plan), including migration activities. A key part of the cut-over planning is to define cut-off dates for transactions in the old system. | Cut-Over Plan | Customer, Implementation Partner
| System change announcement | Inform organization about upcoming system change | Email communication | Customer
| Environment deployment to Production instance | Environment deployment to Production instance | - | Implementation Partner
| Data cleansing | Data cleansing in the old system should be started as early as possible. This applies both to master data such as customer master data as well as transactional data such as open purchase orders - these should ideally be closed/cancelled in the old system to simplify the final migration into the production system. | - | Customer
| Migration of Master Data | Relevant master data such as customers, vendors or products/materials are migrated into the production instance. The customer team has to verify the migration result before the system can be released to end users. | Migration Templates | Implementation Partner
| Migration of Transactional Data | Relevant transactional data such as sales orders, POs, G/L items, opening balances and so on are migrated into the production instance. The customer team has to verify the migration result before the system can be released to end users. | Migration Templates | Implementation Partner
| Go/No-Go Decision | Check if you are ready for go-live: 1. System technically ready? 2. Necessary data migrated successfully? Data has been verified? 3. User accounts setup, users have been properly trained? 4. Interfaces established and working? 5. Implementation Partner is able to provide necessary onsite support? | - | Customer, Implementation Partner
| Go-Live | Release system to end-users, perform go-live | - | Customer
8. CLOSING | Post-Go-Live Support | Provide post go-live support for the agreed period | - | Implementation Partner
| Support handover | After the go-live period, the IT and business support of Dynamics users should be transferred to the customer-side teams | - | Customer
| Lessons Learned | It is good practice to perform a lessons learned workshop after the project and to gather ideas on how to improve project execution in future projects. | - | Customer, Implementation Partner

## Gantt Chart
Dynamics 365 Business Central Implementation Schedule (Sample)
Version: 2.0
| Business | IT | % complete | Oct | Nov | Dec | Jan | Feb | Mar | Apr | May | Jun | Jul | Aug | Sep | Oct | Nov | Dec | Jan | Feb | Mar | Apr | May
National holidays
Local holidays
PROJECT INITIATION
Define project goal and scope | X | X | 100%
Perform stakeholder analysis | X | X
Set up project team | X | X
Acquire software license | X | X
Choose Implementation Partner | X | X
PLANNING PHASE
Create Project Schedule | X | X | 70%
Set up Budget | X | X | 20%
Perform Risk Assessment | X | X
Create Project Charter | X | X
Project Approval | X | X
Project Kickoff Meeting | X | X
DISCOVERY PHASE
Gather Requirements (workshops) | X | X | 70%
Create Requirement Specification Document | X | X | 20%
Review Requirement Specification with customer | X | X | 0%
Requirement Specification Signed off (by customer) | X |  | 0%
DESIGN PHASE
Create Solution Design Document (SDD) |  | X
Review SDD with customer | X | X
Provide effort estimation (for GAPS and configuration) |  | X
Solution Design Document (SDD) Signed off (by customer) | X
DEVELOPMENT PHASE
Create DEV environments |  | X
Create users, user permission sets | X | X
Receive initial data from customer | X | X
Configure DEV environment: System Configuration, Setup | X | X
Business Central Essentials License
Component setup: Financial Management |  | X
Component setup: Sales |  | X
Component setup: Purchasing |  | X
Component setup: Warehouse Management |  | X
Component setup: CRM |  | X
Component setup: Human Resources Management |  | X
Component setup: Projects |  | X
Business Central Premium License
Component setup: Business Central Essentials |  | X
Component setup: Service |  | X
Component setup: Manufacturing |  | X
D365 BC custom development |  | X
Initial data Import |  | X
Define test cases for Functional Test | X
Perform Functional Test | X | X
Bug-fixing & closing of open defects | X | X
Perform SIT (System Integrated Testing) and deliver SIT report | X | X
Bug-fixing & closing of open defects | X | X
SIT Signed off (from customer) | X | X
DEPLOYMENT PHASE
Environment deployment -UAT |  | X
Superuser Training (train the trainer approach) | X | X
Customer UAT(create test case, "penny test" for bank transfers) | X | X
Support customer during UAT | X
UAT signed off. | X
GO LIVE
Inform organization about upcoming change | X
Cut-over Planning | X | X
Environment deployment - PROD | X | X
Data cleansing | X | X | 0%
Migration master data | X | X | 0%
Migrate transactional data (Opening Balances) | X | X
Go/No-Go Decision | X
Go-Live | X | X
PROJECT CLOSING
Hypercare Period | X | X
Post Go-Live Support | X | X
Handover to support team | X | X
Perform Lessons Learned | X | X
Project Closure | X | X

## User Template
Type | First name | Last name | Department | Role | Email address | Fax number | Initial password
User | Rebecca | Simpson | Finance | Accounts Payable Keyuser | rebecca.simpson@companyname.com | 1 (323) 3884-123 | someinitialpassword1777
User | Ken | Williams | Finance | Accounts Payable User | ken.williams2@companyname.com | 1 (323) 3884-123 | someinitialpassword2334
User | Forest | Gump | Sales | Sales Team Lead | forest.gump@companyname.com | 1 (323) 3884-124 | someinitialpassword7134
Admin | Stacey | Cruz | CEO Office | Executive Assistant | stacey.cruz@companyname.com | 1 (323) 3884-200 | someinitialpassword9745

## Vendor Template
Vendors
Name | Street | House number | Postal code (ZIP) | City | Region/State | Country
Sierra Injection Systems | Farnham St. | 401 | 23287 | Muncie | Indiana | US
Bosch Automotive Systems | Robert Bosch Str. | 170 | 70560 | Stuttgart | Baden-Wuerttemberg | DE
Cherokee Spare Parts Inc. | Picadilly Circus | 4202 | 87322 | London | London | UK
Bridgestone Consulting LLC | Miramar Dr. | 761 | 52984 | Fresno | California | US

## Customer Template
Customers
Name | Street | House number | Postal code (ZIP) | City | Region/State | Country
Rubys Diner | Farnham St. | 401 | 23287 | Muncie | Indiana | US
Bosch Automotive Systems | Robert Bosch Str. | 170 | 70560 | Stuttgart | Baden-Wuerttemberg | DE
Cheyenne Parts Inc. | Picadilly Circus | 4202 | 87322 | London | London | UK
Bridgestone Consulting LLC | Miramar Dr. | 761 | 52984 | Fresno | California | US

## Test Case Template
Test Case Template |  |  |  |  | Test name: | <name>
| Use the Test Case Template to define the relevant test cases for the organization. |  |  |  | Date: | <date>
[5 empty] | Project Manager: | <date>
AREA | NO. | TEST CASE | STEP | DESCRIPTION | STATUS | EXPECTED RESULT | ACTUAL RESULT | Comment
Logistics | 1 | Delivery
|  |  | 1 | Create delivery | passed | delivery is created without errors
|  |  | 2 | Print delivery form | failed | form is printed correctly | Logo is missing on the form
|  |  | 3 | Print shipping label | in work | label is printed correctly
|  |  | 4 | Notify freight forwarder | open | freight forwarder informed
|  |  | 5 | Freight forwarder picks up delivery | open | delivery picked up successfully
Accounting | 2 | Billing
|  |  | 1 | Select customer delivery | failed | delivery can be selected | unable to find delivery
|  |  | 2 | Print invoice | in work | invoice is printed correctly
|  |  | 3 | Send invoice to customer | open | invoice sent successfully
|  |  | 4 | Create open item in AR | open | new open item is created without problems
Sales | 3 | Customer master data
|  |  | 1 | Create new customer | passed | new customer is created
|  |  | 2 | Change customer data | passed | customer changed
|  |  | 3 | Block customer | failed | customer blocked | I'm getting a 'missing authorization' error
|  |  | 4 | Delete customer | in work | customer deleted
… | … | …
|  |  | 1 | … | open | …
|  |  | 2 | … | open | …
|  |  | 3 | … | open | …
|  |  | 4 | … | open | ..